## Tracker
Case | Rank | Title | Publish date | Day | Tool(s) | Finished project | Terms note | Script | Tool terms checked | Voice-over | Screen recording | Edit | Thumbnail | Subtitles EN | Subtitles AR | Subtitles UR | Starter files | Web page ready | Uploaded & scheduled | Notes
Trailer | — | Trailer (60 sec) | 2026-10-20 | Tue | Screen recording | Channel trailer |  | Done | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
1 | Rookie | The Screen-Time Case | 2026-10-27 | Tue | Google Forms + Sheets | Anonymous survey, average vs median |  | Done | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Done | Not started | Not started
2 | Rookie | Charts That Lie | 2026-10-27 | Tue | Google Sheets | Same data, honest vs cut-axis vs cherry-picked charts |  | Done | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Done | Not started | Not started
3 | Rookie | Does Money Buy Happiness? | 2026-10-30 | Fri | Gapminder Tools (free, browser) | Two-country claim and what it can't prove | Checked 2026-10-02: CC BY credit needed; confirm commercial use with Gapminder; keep name out of title | Done | In progress | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
4 | Rookie | Correlation Isn't Guilty | 2026-11-03 | Tue | Google Sheets | Third variable and chance links |  | Done | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Done | Not started | Not started
5 | Rookie | The Biased Sample | 2026-11-06 | Fri | Google Sheets | Why surveying only friends misleads |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
6 | Rookie | The Missing Data Mystery | 2026-11-10 | Tue | Google Sheets | Who didn't answer, and why it matters |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
7 | Rookie | Fix the Messy Dataset | 2026-11-13 | Fri | Google Sheets | Clean typos, duplicates, wrong units |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
8 | Rookie | Finale: Build Your Own Case | 2026-11-17 | Tue | Forms + Sheets | One-page case file from your own question |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
9 | Analyst | Teach a Machine | 2026-11-20 | Fri | Teachable Machine | Image or pose classifier (no faces) | Verified (Google blog): examples stay on device unless saved to Drive. NOT verified: site terms, age rules, commercial use. Read the footer Terms and Privacy on filming day. | In progress | In progress | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
10 | Analyst | Break the AI | 2026-11-24 | Tue | Teachable Machine | Log of ways the model gets fooled | Same tool as Case 9: read footer Terms/Privacy on filming day. Adversarial-example claim sourced to Goodfellow, Shlens, Szegedy 2014 (arXiv 1412.6572). | In progress | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
11 | Analyst | Training vs Testing | 2026-11-27 | Fri | Teachable Machine / ML tool | Why you test on examples the model hasn't seen |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
12 | Analyst | The Biased Hiring Bot | 2026-12-01 | Tue | No-code ML tool (to choose) | Model that learns an unfair pattern (made-up data) |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
13 | Analyst | Real or Fake? | 2026-12-04 | Fri | Screen demos only | Spotting checklist and quiz game | Answer altered-content question in Studio | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
14 | Analyst | Interrogate the Chatbot | 2026-12-08 | Tue | Chatbot demo (adult account) | Fact-check an AI answer | Check age rules of the chatbot used | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
15 | Analyst | Predict It (No Code) | 2026-12-11 | Fri | No-code ML tool (to choose) | A first prediction on made-up data |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
16 | Analyst | Finale: Build and Break Your Model | 2026-12-15 | Tue | Tools so far | Train a model, then find its weak spot |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
17 | Inspector | Hello, Python | 2026-12-18 | Fri | Browser Python notebook (to choose) | First lines of Python | Check sign-in and age rules | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
18 | Inspector | Load the Evidence | 2026-12-22 | Tue | Python + pandas | Load the Case 1 data from CSV |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
19 | Inspector | Clean It With Code | 2026-12-25 | Fri | Python + pandas | Redo Case 7 in code |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
20 | Inspector | Chart It With Code | 2026-12-29 | Tue | Python + matplotlib | Redo honest charts from Case 2 |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
21 | Inspector | Correlation in Code | 2027-01-01 | Fri | Python + pandas | Redo Case 4 incl. the chance table |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
22 | Inspector | Your First Prediction | 2027-01-05 | Tue | Python + scikit-learn | Simple regression |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
23 | Inspector | Test Your Model | 2027-01-08 | Fri | Python + scikit-learn | Train/test split, overfitting |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
24 | Inspector | Finale: A Reproducible Case File | 2027-01-12 | Tue | Notebook | One notebook anyone can re-run |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
25 | Chief | Choose Your Case | 2027-01-15 | Fri | Planning sheet | Question, data plan, limits |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
26 | Chief | Find Real Data | 2027-01-19 | Tue | Open data portals (to choose) | Pick a dataset and check its terms | Check each source's license | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
27 | Chief | Collect Data Ethically | 2027-01-22 | Fri | Forms | Consent, anonymity, privacy plan |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
28 | Chief | Analyze It | 2027-01-26 | Tue | Sheets or Python | Full analysis of your question |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
29 | Chief | Tell the Story | 2027-01-29 | Fri | Chart/dashboard tool (to choose) | Honest visual summary | Check the tool's terms | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
30 | Chief | Check Your Own Work | 2027-02-02 | Tue | Your notebook or sheet | Three questions + limitations |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
31 | Chief | Present Your Case | 2027-02-05 | Fri | Screen recording | A 3-minute case presentation |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started
32 | Chief | Finale: Case Review | 2027-02-09 | Tue | Viewer work (with consent) | Featured projects, no names/faces |  | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started | Not started

## Summary
RED STRINGS LAB · 32-case roadmap
Blue = typed-in inputs. Change dates on the Tracker tab if holidays or illness move things.
Rank | Cases | Scripts done | Uploaded & scheduled | First publish | Last publish
Rookie | 8 | 4 | 0 | 2026-10-27 | 2026-11-17
Analyst | 8 | 0 | 0 | 2026-11-20 | 2026-12-15
Inspector | 8 | 0 | 0 | 2026-12-18 | 2027-01-12
Chief | 8 | 0 | 0 | 2027-01-15 | 2027-02-09
Total | 32 | 4 | 0
PRODUCTION PLAN (first 3 weeks)
Week of 5 Oct | Trailer, Case 1, Case 2 (scripts already written)
Week of 12 Oct | Cases 3, 4, 5
Week of 19 Oct | Cases 6, 7, 8, subtitles, upload and schedule everything by Fri 23 Oct
Rule | Always stay 2 to 4 weeks ahead. Keep 2 spare cases unscheduled for emergencies.
SPARE CASES (not scheduled)
Spare A | Case 00: What is a dataset? (rows, columns, a 2-minute orientation)
Spare B | To decide
Formulas:
First publish = INDEX(Tracker!$D2:D34,MATCH([Rank],Tracker!$B2:B34,0))
Last publish = INDEX(Tracker!$D2:D34,MATCH([Rank],Tracker!$B2:B34,0)+COUNTIF(Tracker!$B2:B34,[Rank])-1)